## BETA 1.0
Functionality | Module | Beta(1.0) | 2014-05-08 | Comments from 5/8/2014 | 2014-06-09 | Comments from 6/9/2014
Contacts | Contacts | Y
Individual contacts | Contacts | Y
Add New contact | Contacts | Y | DEV |  | COMPLETED | * Email Status Update
Duplicate Contact found – Save as New contact | Contacts | Y | DEV |  | COMPLETED | * CR Pending
Send email, VoIP, SMS, and Social Media | Contacts | Y
Send email | Contacts | Y | DEV |  | DEV
Send SMS | Contacts | Y | DEV |  | DEV
Associate one or more tag(s) with a contact | Contacts | Y | DEV |  | DEV
Create a new tag | Contacts | Y | MISSED | Grant gave ISD on 03/26 | MISSED | Grant gave ISD on 03/26
Create a reminder | Contacts | Y | DEV |  | DEV
Identifies the meeting as a property tour | Contacts | Y | DEV |  | DEV
View reminders and meetings in list or calendar view | Contacts | Y | NOT STARTED |  | NOT STARTED
Identify reminders that are overdue | Contacts | Y | NOT STARTED |  | NOT STARTED
Record completion of a reminder | Contacts | Y | DEV |  | DEV
Record information on communities toured by contact | Contacts | Y | DEV |  | DEV
Create and attach a note to a contact | Contacts | Y | DEV |  | DEV
View a history of interactions with a contact | Contacts | Y | DEV | CR's PENDING | DEV | CR's PENDING
Link to a person's social media profile | Contacts | Y | DEV |  | DEV
View a person's social media profile | Contacts | Y | DEV |  | DEV
Associate people with one another and define their relationship | Contacts | Y | DEV |  | DEV
Associate a Dropbox file with a person | Contacts | Y | DEV |  | DEV
Company Contact | Contacts | Y
Add New company's contact information | Contacts | Y | DEV |  | DEV
Duplicate Company found – Save as New Company | Contacts | Y | DEV |  | DEV
Contact Additional Features | Contacts | Y
Create a new contact by copying an existing contact | Contacts | Y | NOT STARTED |  | NOT STARTED
Search for a person | Contacts | Y | DEV |  | DEV
Export a person | Contacts | Y | NOT STARTED |  | NOT STARTED
Delete a person | Contacts | Y | DEV |  | DEV
Groups of People | Contacts | Y
View a list of contacts | Contacts | Y | DEV |  | DEV
View a list of my contacts | Contacts | Y | NOT STARTED |  | NOT STARTED
Search for contacts using one or more criteria | Contacts | Y | NOT STARTED |  | NOT STARTED
Export a group of people from search results | Contacts | Y | NOT STARTED |  | NOT STARTED
Add or remove tag within search results | Contacts | Y | NOT STARTED |  | NOT STARTED
Create an action item for a group of people | Contacts | Y | DEV |  | DEV
Create an action item to contact a group of people | Contacts | Y | DEV |  | DEV
Create a task associated with a group of people | Contacts | Y | DEV |  | DEV
Delete a group of people | Contacts | Y | NOT STARTED |  | NOT STARTED
Cancel an action and return to search results | Contacts | Y | NOT STARTED |  | NOT STARTED
Marketing |  | Y
Templates | Campaigns | Y | DEV |  | DEV
Campaigns | Campaigns | Y
Campaign Builder | Campaigns | Y
Create an email campaign with a drag & drop editor | Campaigns | Y | DEV |  | DEV
Upload an image for use in emails | Campaigns | Y | DEV |  | DEV
Email a group of people | Campaigns | Y | DEV |  | DEV
Schedule an email to a group of people | Campaigns | Y | DEV |  | DEV
Track email interactions | Campaigns | Y
Track an Email Recipient opening an email | Campaigns | Y | NOT STARTED |  | NOT STARTED
Track an Email Recipient clicking a link | Campaigns | Y | NOT STARTED |  | NOT STARTED
Lead Capture | Forms | Y
Connect third-party lead generation sites for lead capture from external sources | Administration | Y | IN PROGRESS |  | IN PROGRESS
X - Map third-party lead adapter forms to SmartTouch forms | Administration | Y | IN PROGRESS |  | IN PROGRESS
Create a lead-capture form | Forms | Y | IN PROGRESS |  | IN PROGRESS
Generate embed code for a lead-capture form | Forms | Y | IN PROGRESS |  | IN PROGRESS
Copies form code to clipboard | Forms | Y | IN PROGRESS |  | IN PROGRESS
View leads that submitted a form | Forms | Y | IN PROGRESS |  | IN PROGRESS
Determine how Sales Users are notified of incoming leads | Automation | Y | IN PROGRESS |  | IN PROGRESS
Opts to notify selected Sales Users of incoming leads | Automation | Y | IN PROGRESS |  | IN PROGRESS
Automation Workflow | Automation | Y
Create automation workflow to trigger actions based on an interaction | Automation | Y
Trigger workflow when a form is submitted | Automation | Y | NOT STARTED |  | NOT STARTED
Trigger workflow when a Contact's lifecycle changes | Automation | Y | NOT STARTED |  | NOT STARTED
Trigger workflow when a tag is applied | Automation | Y | NOT STARTED |  | NOT STARTED
Trigger workflow when a link is clicked | Automation | Y | NOT STARTED |  | NOT STARTED
Send an email | Automation | Y | NOT STARTED |  | NOT STARTED
Set a delay timer | Automation | Y | NOT STARTED |  | NOT STARTED
Set a date timer | Automation | Y | NOT STARTED |  | NOT STARTED
Add a tag | Automation | Y | NOT STARTED |  | NOT STARTED
Remove a tag | Automation | Y | NOT STARTED |  | NOT STARTED
Adjust a Contact's lead score | Automation | Y | NOT STARTED |  | NOT STARTED
Change a Contact's lifecycle | Automation | Y | NOT STARTED |  | NOT STARTED
Update a contact field | Automation | Y | NOT STARTED |  | NOT STARTED
Assign a Contact to a User | Automation | Y | NOT STARTED |  | NOT STARTED
Notify a User or Group | Automation | Y | NOT STARTED |  | NOT STARTED
Add a task/action/reminder | Automation | Y | NOT STARTED |  | NOT STARTED
Send a text message | Automation | Y | NOT STARTED |  | NOT STARTED
Configure micro-workflows attached to links within an email | Automation | Y | NOT STARTED |  | NOT STARTED
Configure automation workflow settings | Automation | Y | NOT STARTED |  | NOT STARTED
Select predefined automation workflow recipes | Automation | Y | NOT STARTED |  | NOT STARTED
Reporting & Analytics | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Run Smart Reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Create an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Export an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Save an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Save results of a search as a report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Access recently-run reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Run a stock report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Web-tracking | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Track web visits with Visistat | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED
Administration | Administration
Login | Administration | Y | DEV |  | DEV
Disables the ‘Show password as I type’ checkbox | Administration | Y |  | Removed Functionality |  | Removed Functionality
Enters an invalid password | Administration | Y | DEV |  | DEV
Enters an invalid email | Administration | Y | DEV |  | DEV
Reset login credentials | Administration | Y | DEV |  | DEV
Enters a valid email and requests a sign-in link | Administration | Y | DEV |  | DEV
Enters an invalid password | Administration | Y | DEV |  | DEV
Setup & Customization | Administration | Y
Create a new account | Administration | Y | DEV | IIS Script for Auto Domain Binding | DEV | IIS Script for Auto Domain Binding
Continue configuration within customer’s account | Administration | Y | DEV |  | DEV
Send contact a welcome email | Administration | Y | DEV | Account Creation Email Pending | DEV | Account Creation Email Pending
On-board new account | Administration | Y | DEV |  | DEV
Configure lead scoring | Administration | Y | IN PROGRESS |  | IN PROGRESS
Create custom fields | Administration | Y | NOT STARTED |  | NOT STARTED
Set default pagination for tables | Administration | Y | IN PROGRESS |  | IN PROGRESS
Internationalize form elements | Administration | Y | IN PROGRESS |  | IN PROGRESS
Localize SmartTouch | Administration | Y | IN PROGRESS |  | IN PROGRESS
Link social media accounts with SmartTouch | Administration | Y | NOT STARTED | Also needs info from Grant | NOT STARTED | Also needs info from Grant
Import a list of data | Administration | Y | IN PROGRESS |  | IN PROGRESS
Roles and Permissions | Administration | Y
Create roles and permissions | Administration | Y | IN PROGRESS |  | IN PROGRESS
Identify a contact as a SmartTouch user | Administration | Y | IN PROGRESS |  | IN PROGRESS
Change a user’s role via setup | Administration | Y | IN PROGRESS |  | IN PROGRESS
Integrations | Integrations | Y
Gmail | Integrations | Y | NOT STARTED |  | NOT STARTED
Google Calendar | Integrations | Y | NOT STARTED |  | NOT STARTED
Office365 | Integrations | Y | OUT OF SCOPE FOR US |  | OUT OF SCOPE FOR US
Outlook 2007 (or maybe 2010?) | Integrations | Y | OUT OF SCOPE FOR US |  | OUT OF SCOPE FOR US
Google Maps | Integrations | Y | NOT STARTED |  | NOT STARTED
Zillow Homes | Integrations | Y | IN PROGRESS | Lead Adaptors | IN PROGRESS | Lead Adaptors
Email lookup | Integrations | Y | NOT STARTED |  | NOT STARTED