## BETA 1.0
Functionality | Module | Beta(1.0) | 2014-05-08 | Comments from 5/8/2014 | 2014-06-09 | Comments from 6/9/2014
Contacts | Contacts | Y |  |  |  |  | Completed
Individual contacts | Contacts | Y |  |  |  |  | Completed
Add New contact | Contacts | Y | DEV |  | COMPLETED | * Email Status Update | Completed
Duplicate Contact found – Save as New contact | Contacts | Y | DEV |  | COMPLETED | * CR Pending | Completed - Email OR Fname +Lname + Email ; Email OR Email+Company Name OR Company Name
Send email, VoIP, SMS, and Social Media | Contacts | Y |  |  |  |  | Completed
Send email | Contacts | Y | DEV |  | DEV |  | Completed
Send SMS | Contacts | Y | DEV |  | DEV |  | Completed
Associate one or more tag(s) with a contact | Contacts | Y | DEV |  | DEV |  | Completed
Create a new tag | Contacts | Y | MISSED | Grant gave ISD on 03/26 | MISSED | Grant gave ISD on 03/26 | Completed
Create a reminder | Contacts | Y | DEV |  | DEV |  | Completed
Identifies the meeting as a property tour | Contacts | Y | DEV |  | DEV |  | Completed - Tours With Reminders
View reminders and meetings in list or calendar view | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Calender Integration - UnderProgress
Identify reminders that are overdue | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Calender Integration - UnderProgress
Record completion of a reminder | Contacts | Y | DEV |  | DEV |  | Completed - Action Mark As Complete
Record information on communities toured by contact | Contacts | Y | DEV |  | DEV |  | Completed - Timelines
Create and attach a note to a contact | Contacts | Y | DEV |  | DEV |  | Completed
View a history of interactions with a contact | Contacts | Y | DEV | CR's PENDING | DEV | CR's PENDING | Completed - Timelines
Link to a person's social media profile | Contacts | Y | DEV |  | DEV |  | Completed - Timelines
View a person's social media profile | Contacts | Y | DEV |  | DEV |  | Scoped Out As on 20/12/2013
Associate people with one another and define their relationship | Contacts | Y | DEV |  | DEV |  | Completed
Associate a Dropbox file with a person | Contacts | Y | DEV |  | DEV |  | Attachments - Dropbox / Google Drive Integrations
Company Contact | Contacts | Y |  |  |  |  | Completed
Add New company's contact information | Contacts | Y | DEV |  | DEV |  | Completed
Duplicate Company found – Save as New Company | Contacts | Y | DEV |  | DEV |  | Completed
Contact Additional Features | Contacts | Y |  |  |  |  | Completed
Create a new contact by copying an existing contact | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Search for a person | Contacts | Y | DEV |  | DEV |  | Completed
Export a person | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Delete a person | Contacts | Y | DEV |  | DEV |  | Completed
Groups of People | Contacts | Y |  |  |  |  | Completed
View a list of contacts | Contacts | Y | DEV |  | DEV |  | Completed
View a list of my contacts | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Search for contacts using one or more criteria | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Export a group of people from search results | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Add or remove tag within search results | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Create an action item for a group of people | Contacts | Y | DEV |  | DEV |  | Completed
Create an action item to contact a group of people | Contacts | Y | DEV |  | DEV |  | Completed
Create a task associated with a group of people | Contacts | Y | DEV |  | DEV |  | Completed
Delete a group of people | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Cancel an action and return to search results | Contacts | Y | NOT STARTED |  | NOT STARTED |  | Completed
Marketing |  | Y |  |  |  |  | Completed
Templates | Campaigns | Y | DEV |  | DEV |  | Completed
Campaigns | Campaigns | Y |  |  |  |  | Completed
Campaign Builder | Campaigns | Y |  |  |  |  | Completed
Create an email campaign with a drag & drop editor | Campaigns | Y | DEV |  | DEV |  | Completed
Upload an image for use in emails | Campaigns | Y | DEV |  | DEV |  | Completed
Email a group of people | Campaigns | Y | DEV |  | DEV |  | Completed
Schedule an email to a group of people | Campaigns | Y | DEV |  | DEV |  | Completed
Track email interactions | Campaigns | Y |  |  |  |  | Completed
Track an Email Recipient opening an email | Campaigns | Y | NOT STARTED |  | NOT STARTED |  | Completed
Track an Email Recipient clicking a link | Campaigns | Y | NOT STARTED |  | NOT STARTED |  | Completed
Lead Capture | Forms | Y |  |  |  |  | Completed
Connect third-party lead generation sites for lead capture from external sources | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
X - Map third-party lead adapter forms to SmartTouch forms | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Create a lead-capture form | Forms | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Generate embed code for a lead-capture form | Forms | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Copies form code to clipboard | Forms | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
View leads that submitted a form | Forms | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Determine how Sales Users are notified of incoming leads | Automation | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Opts to notify selected Sales Users of incoming leads | Automation | Y | IN PROGRESS |  | IN PROGRESS |  | Completed - Notifies the Account Admin - When Admin Assigns to Individual Sales Users
Automation Workflow | Automation | Y |  |  |  |  | Under Progress
Create automation workflow to trigger actions based on an interaction | Automation | Y |  |  |  |  | Under Progress
Trigger workflow when a form is submitted | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Trigger workflow when a Contact's lifecycle changes | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Trigger workflow when a tag is applied | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Trigger workflow when a link is clicked | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Send an email | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Set a delay timer | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Set a date timer | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Add a tag | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Remove a tag | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Adjust a Contact's lead score | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Change a Contact's lifecycle | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Update a contact field | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Assign a Contact to a User | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Notify a User or Group | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Add a task/action/reminder | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Send a text message | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Configure micro-workflows attached to links within an email | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Configure automation workflow settings | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Select predefined automation workflow recipes | Automation | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Reporting & Analytics | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Run Smart Reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Create an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Export an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Save an ad-hoc report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Save results of a search as a report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Access recently-run reports | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Run a stock report | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Under Progress
Web-tracking | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Completed
Track web visits with Visistat | Reporting & Analytics | Y | NOT STARTED |  | NOT STARTED |  | Completed
Administration | Administration | [5 empty] | Completed
Login | Administration | Y | DEV |  | DEV |  | Completed
Disables the ‘Show password as I type’ checkbox | Administration | Y |  | Removed Functionality |  | Removed Functionality | Scoped Out As on 20/12/2013
Enters an invalid password | Administration | Y | DEV |  | DEV |  | Completed
Enters an invalid email | Administration | Y | DEV |  | DEV |  | Completed
Reset login credentials | Administration | Y | DEV |  | DEV |  | Completed
Enters a valid email and requests a sign-in link | Administration | Y | DEV |  | DEV |  | Completed
Enters an invalid password | Administration | Y | DEV |  | DEV |  | Completed
Setup & Customization | Administration | Y |  |  |  |  | Completed
Create a new account | Administration | Y | DEV | IIS Script for Auto Domain Binding | DEV | IIS Script for Auto Domain Binding | Completed
Continue configuration within customer’s account | Administration | Y | DEV |  | DEV |  | Completed
Send contact a welcome email | Administration | Y | DEV | Account Creation Email Pending | DEV | Account Creation Email Pending | Completed
On-board new account | Administration | Y | DEV |  | DEV |  | Completed
Configure lead scoring | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Create custom fields | Administration | Y | NOT STARTED |  | NOT STARTED |  | Completed
Set default pagination for tables | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed - Logged in sales user settings
Internationalize form elements | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed - TimeZone Settings
Localize SmartTouch | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed - TimeZone Settings
Link social media accounts with SmartTouch | Administration | Y | NOT STARTED | Also needs info from Grant | NOT STARTED | Also needs info from Grant | Scoped Out As on 20/12/2013
Import a list of data | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Roles and Permissions | Administration | Y |  |  |  |  | Completed
Create roles and permissions | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Identify a contact as a SmartTouch user | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Change a user’s role via setup | Administration | Y | IN PROGRESS |  | IN PROGRESS |  | Completed
Integrations
Gmail | Integrations | Y | OUT OF SCOPE FOR US |  | OUT OF SCOPE FOR US |  | Scope Not Defined
Google Calendar | Integrations | Y | OUT OF SCOPE FOR US |  | OUT OF SCOPE FOR US |  | Scope Not Defined
Office365 | Integrations | Y |  |  |  |  | Scope Not Defined
Outlook 2007 (or maybe 2010?) | Integrations | Y | NOT STARTED |  | NOT STARTED |  | Scope Not Defined
Google Maps | Integrations | Y | IN PROGRESS | Lead Adaptors | IN PROGRESS | Lead Adaptors | Scope Not Defined
Zillow Homes | Integrations | Y | NOT STARTED |  | NOT STARTED |  | Scope Not Defined
Email lookup | Integrations | Y |  |  |  |  | Scope Not Defined

## Sheet1
Communication Providers
Account Header
MailChimp
SendGrid
Google Drive
DropBox
Entitlements
Opportunities