## 7-4-2014
Task Name | Duration | Planned Work | Actual Work | Pending Work
Design & Develop Opportunities Module | 30 days | 610 hrs
Design Review and Finalize Data Model | 3 days | 50 hrs | 30 hrs | 20 hrs
Integration of Final UI from Prototypes | 1 day | 60 hrs | 50 hrs | 10 hrs
Development of Module | 30 days | 325 hrs | 50 hrs | 275 hrs
Functional Testing of Module | 5 days | 100 hrs |  | 100 hrs
Bug Fixing & Stabilize code for Landing Pages | 2 days | 75 hrs |  | 75 hrs
Enhancements on Existing Modules | 6 days | 184hrs
Tags | 2 days | 40 hrs | 10 hrs | 30 hrs
Dashboards | 4 days | 20 hrs |  | 20 hrs
Contacts | 2 days | 36 hrs | 12 hrs | 24 hrs
Reports | 4 days | 40 hrs |  | 40 hrs
Account Manager | 1 day | 16 hrs | 10 hrs | 6 hrs
Account Settings | 1 day | 8 hrs | 8 hrs | 0 hrs
Entitlements | 2 days | 24 hrs | 16 hrs | 8 hrs
TOTAL ESTIMATE | 36 Days | 794 hrs | 186 hrs | 608 hrs