## June - Work
| 2014-05-30 |  | 2014-06-06 |  | 2014-06-13 |  | 2014-06-20 |  | 2014-06-27 |  | 2014-07-04 |  |  | Monthly Hrs Spent
Task Name | Actual Work | Pending Hours | Actual Work | Pending Hours | Actual Work | Pending Hours | Actual Work | Pending Hours | Actual Work | Pending Hours | Actual Work | Pending Hours |  |  |  | 146
Design & Develop Contacts Module | 625 hrs | 50 hrs | 625 hrs | 50 hrs | 625 hrs | 50 hrs | 625 hrs | 50 hrs | 625 hrs | 50 hrs | 625 hrs | 50 hrs | 50 | 50 | 0 | 25
Design & Develop Campaigns Module | 680 hrs | 115 hrs | 680 hrs | 115 hrs | 680 hrs | 115 hrs | 680 hrs | 115 hrs | 705 hrs | 90 hrs | 705 hrs | 90 hrs | 115 | 90 | 25 | 155
Design & Develop Marketing Automation Module | 0 hrs | 840 hrs | 0 hrs | 840 hrs | 0 hrs | 840 hrs | 0 hrs | 840 hrs | 0 hrs | 840 hrs | 0 hrs | 840 hrs | 840 | 840 | 0 | 160
Design & Develop Internet Forms/Lead Captures Module | 445 hrs | 345 hrs | 495 hrs | 300 hrs | 505 hrs | 290 hrs | 555 hrs | 240 hrs | 605 hrs | 190 hrs | 630 hrs | 165 hrs | 345 | 165 | 180 | 145
Design & Develop Personal Settings Module | 490 hrs | 365 hrs | 515 hrs | 340 hrs | 560 hrs | 295 hrs | 560 hrs | 295 hrs | 605 hrs | 250 hrs | 635 hrs | 220 hrs | 365 | 220 | 145 | 180
Design & Develop Account Admin Settings Module | 460 hrs | 360 hrs | 535 hrs | 285 hrs | 570 hrs | 250 hrs | 620 hrs | 200 hrs | 620 hrs | 200 hrs | 620 hrs | 200 hrs | 360 | 200 | 160 | 80
Design & Develop Super Admin - Accounts Management Module | 584.98 hrs | 325 hrs | 584.98 hrs | 325 hrs | 630 hrs | 280 hrs | 674.98 hrs | 235 hrs | 709.98 hrs | 200 hrs | 740.02 hrs | 170 hrs | 325 | 170 | 155 | 180
Design & Develop Account Dashboard Module | 0 hrs | 800 hrs | 0 hrs | 800 hrs | 0 hrs | 800 hrs | 0 hrs | 800 hrs | 0 hrs | 800 hrs | 0 hrs | 800 hrs | 800 | 800 | 0 | 50
Design & Develop Account Reports Module | 0 hrs | 950 hrs | 0 hrs | 950 hrs | 0 hrs | 950 hrs | 0 hrs | 950 hrs | 0 hrs | 950 hrs | 0 hrs | 950 hrs | 950 | 950 | 0 | 186
Design & Develop 3rd Party Components and Integrations | 445 hrs | 495 hrs | 500 hrs | 440 hrs | 555 hrs | 385 hrs | 575 hrs | 365 hrs | 610 hrs | 330 hrs | 645 hrs | 295 hrs | 495 | 295 | 200 | 200
Open API to third party developers | 25 hrs | 175 hrs | 25 hrs | 175 hrs | 35 hrs | 165 hrs | 50 hrs | 150 hrs | 75 hrs | 125 hrs | 75 hrs | 125 hrs | 175 | 125 | 50 | 170
Integrations | 80 hrs | 525 hrs | 80 hrs | 525 hrs | 80 hrs | 525 hrs | 120 hrs | 485 hrs | 160 hrs | 445 hrs | 190 hrs | 445 hrs | 525 | 445 | 80 | 1677 | 79.8571 | 11.4082
995
Hari
[7 empty] | Bharath | Ramana | [5 empty] | 1677
[7 empty] | NM | Mamata | [5 empty] | 76.2273
[7 empty] | Srinivas | Sankeerth | [5 empty] | 9.5284
[7 empty] | mall | Pramodh
Siva
Avinah
Haritha
Bhavani
Naresh