## Sheet1
Module Name | CR# | Summary | Estimated Hrs | Comments
Contacts | 1 | display a Gravator. | 24
Contacts | 2 | Display * for Primary Email, Change the section from Editable to Read only | 24
Contacts | 3 | Attachments Tab View changes | 32
Contacts | 4 | Include Attachments into Timeline - Update action filters | 80
Contacts | 5 | Opportunities as per the current scope provided | 220
Contacts | 6 | Add Tags New Functionality | 40
Campaigns | 1 | New Computed Fields in campaigns grid | 20
Campaigns | 2 | Select and Preview Functionalities | 24
Campaigns | 3 | From and To Functional Update | 40
Campaigns | 4 | Send and Review with new Draft Option for Saving and editing campaigns | 40
Campaigns | 5 | 1. Image Upload / Delete Functionality in Campaign Builder – Customization | 80 | Additional Development done
3. Preview Campaign in Customization Section
Personal Settings | 1 | Saving Personal Settings for Currency formats | 20
Personal Settings | 2 | Saving Personal Settings for Time Zones | 60 | Additional Development done
Account Settings | 1 | Multi Select Dropdowns - Custom Filed Settings | TBD | Needs to discuss with Ashok
Account Settings | 2 | Merge Tags Functional UI Changes - In Line to Pop-up | 8
Account Settings | 3 | Merge Tags Confirmation message with the count of contacts merged | 8
Forms | 1 | Adding Custom Fields to Form Builder | TBD | Needs to discuss with Ashok
Forms | 2 | Add Visibility Options for fields | 40
Forms | 3 | Drag and Drop Functionality for Fields - in Form Builder | 40
Automation | 1 | Include "Send Text" in Actions | 24
Automation | 2 | In Add/Edit Workflow>>Assign to User>>Assign via round-robin--check-box--If selected, | 120
Automation | 3 | New Settings for Automation workflows | 80
Automation | 4 | New Field to save Automation Public Description | 16
Email Preferences | 1 | Un Subscription functionality for Contacts | 80 | New Requirement , Not in Priority List
Search | 1 | Updated Functionalities | TBD | Needs to discuss with Ashok
Reports | 1 | Updated Functionalities | TBD | Needs to discuss with Ashok
Dashboards | 1 | Updated Functionalities | TBD | Needs to discuss with Ashok