## Sheet1
ALPHA Release: Excludes Marketing Automation, Reporting |  | Migration Plan
Dev Complete, Integration Testing Complete | 2014-08-01 | Defining the migration startegy
System Testing | 2014-09-06 | Review and design migration Plan
User Acceptance Test | 2014-10-03
GO LIVE | 2014-10-03
BETA Release: Includes both Opportunities, Marketing Automation and Reporting
Dev Complete, Integration Testing Complete | 2014-10-04 | Development completion for migration
System Testing | 2014-11-15 | Migration testing
User Acceptance Test | 2014-11-18 | Migrate the targetted existsing small customers
Migration Readiness | 2014-11-27 | Identify Custom migration plan for new customers
GO LIVE | 2014-12-30
POST BETA Release: Post Beta Scope and Other CR's + Advanced Entitlement Changes , Additional Automation Triggers |  | * Based on the new customers plan we will proceed with dev and migration
Dev Complete, Integration Testing Complete | 2015-03-14
System Testing | 2015-04-18
User Acceptance Test | 2015-05-23
Migration Readiness | 2015-05-29
GO LIVE | 2015-05-31