## Use Cases
Functionality | Module | Beta(1.0) | 1.1 | 2 | Notes | # | FSD Page #
Contacts | Contacts | Y |  |  |  | 1 | 10
Individual contacts | Contacts | Y |  |  |  | 2 | 10
Add New contact | Contacts | Y |  |  |  | 3 | 10
Duplicate Contact found – Save as New contact | Contacts | Y |  |  |  | 4 | 12
Duplicate Contact found – Merge with Existing contact | Contacts |  |  |  | Future Release | 5 | 12
Send email, VoIP, SMS, and Social Media | Contacts | Y |  |  |  | 6 | 13
Send email | Contacts | Y |  |  |  | 7 | 13
Send VoIP | Contacts |  |  |  | Future Release | 8 | 14
Send SMS | Contacts | Y |  |  |  | 9 | 15
Send Social Media | Contacts |  |  |  | Future Release | 10 | 16
Associate one or more tag(s) with a contact | Contacts | Y |  |  |  | 11 | 17
Create a new tag | Contacts | Y |  |  |  | 12 | 17
Create a reminder | Contacts | Y
Create a meeting | Contacts |  |  |  | Via Integrations and/or Future Release
Sales User adds invites other Sales Users | Contacts |  |  |  | Via Integrations and/or Future Release
Identifies the meeting as a property tour | Contacts | Y
View reminders and meetings in list or calendar view | Contacts | Y
Identify reminders that are overdue | Contacts | Y
Record completion of a reminder | Contacts | Y
Record information on communities toured by contact | Contacts | Y |  |  |  | 20 | 24
Record information on property related to contact | Contacts |  |  |  | custom/extended fields with API with outside inventory | 21 | 24
Create and attach a note to a contact | Contacts | Y |  |  |  | 23 | 25
View a history of interactions with a contact | Contacts | Y |  |  |  | 24 | 26
Link to a person's social media profile | Contacts | Y
View a person's social media profile | Contacts | Y |  |  | Not within out App. FullContact Intergration in Beta | 26 | 27
View a person's social media connections in common with the user | Contacts |  |  |  | Future Release | 27 | 28
View a person's social media conversations | Contacts |  |  |  | Future Release | 28 | 28
Associate people with one another and define their relationship | Contacts | Y |  |  |  | 29 | 29
Add a person to a campaign series | Contacts |  |  |  | Future Release | 30 | 30
Associate a Dropbox file with a person | Contacts | Y |  |  |  | 31 | 30
Associate an uploaded document with a person | Contacts |  |  |  | Future Release | 31 | 30
Upload a new document to associate with a person | Contacts |  |  |  | Future Release | 32 | 31
Share a document with a person | Contacts |  |  |  | Future Release | 33 | 31
Company Contact | Contacts | Y
Add New company's contact information | Contacts | Y |  |  |  | 34 | 32
Duplicate Company found – Save as New Company | Contacts | Y |  |  | May not be needed if we identify duplicates once we have enough information, such as First Name, Last Name, and Email Address. | 35 | 33
Duplicate Company found – Merge with Existing Company | Contacts |  |  |  | Future Release | 36 | 34
Contact Additional Features | Contacts | Y
Create a sales opportunity associated with a contact | Contacts |  | Y |  |  | 37 | 34
Associate people with a sales opportunity and define their relationships | Contacts |  | Y |  |  | 38 | 35
Create a new contact by copying an existing contact | Contacts | Y |  |  |  | 39 | 36
Search for a person | Contacts | Y |  |  |  | 40 | 36
Export a person | Contacts | Y |  |  |  | 41 | 37
Delete a person | Contacts | Y |  |  |  | 41 | 37
Archive a person | Contacts |  |  |  | Future Release | 42 | 37
Restore a person *** | Contacts |  |  |  | Future Release | 43 | 38
Groups of People | Contacts | Y |  |  |  | 44 | 38
View a list of contacts | Contacts | Y |  |  |  | 45 | 38
View a list of my contacts | Contacts | Y |  |  |  | 46 | 39
Synchronize a contact list with my smartphone | Contacts |  |  |  | Via Integrations and/or Future Release | 47 | 39
Search for contacts using one or more criteria | Contacts | Y |  |  |  | 48 | 39
Export a group of people from search results | Contacts | Y |  |  |  | 49 | 41
Add or remove tag within search results | Contacts | Y |  |  |  | 50 | 42
Create an action item for a group of people | Contacts | Y |  |  |  | 51 | 43
Create an action item to contact a group of people | Contacts | Y |  |  |  | 52 | 43
Create a task associated with a group of people | Contacts | Y |  |  |  | 53 | 44
Start/stop a campaign series from search results | Contacts |  |  |  | Future Release | 54 | 45
Assign a group of people to a company from search results | Contacts |  |  |  | see below. Delete if needed | 55 | 46
Update contact field for a group of people | Contacts |  |  |  | Future Release | 56 | 46
Opts to add another field to update | Contacts |  |  |  | Future Release | 57 | 47
Delete a group of people | Contacts | Y |  |  |  | 59 | 48
Archive a group of people from search results | Contacts |  |  |  | Future Release | 58 | 47
Cancel an action and return to search results | Contacts | Y |  |  |  | 59 | 48
Marketing |  | Y |  |  |  | 60 | 48
Templates | Campaigns | Y |  |  |  | 61 | 48
Campaigns | Campaigns | Y |  |  |  | 62 | 48
Campaign Builder | Campaigns | Y
Create an email campaign with a drag & drop editor | Campaigns | Y |  |  |  | 63 | 49
Save email campaign as a template | Campaigns |  |  |  | Initially, templates will all be provide by ST | 64 | 50
Save template and overwrite an existing template | Campaigns |  |  |  | Future Release | 65 | 51
Upload an image for use in emails | Campaigns | Y |  |  |  | 66 | 51
Email a group of people | Campaigns | Y |  |  |  | 67 | 52
Schedule an email to a group of people | Campaigns | Y |  |  |  | 68 | 53
Track email interactions | Campaigns | Y |  |  |  | 69 | 53
Track an Email Recipient opening an email | Campaigns | Y |  |  |  | 70 | 54
Track an Email Recipient clicking a link | Campaigns | Y |  |  |  | 71 | 54
Lead Capture | Forms | Y |  |  |  | 72 | 54
Connect third-party lead generation sites for lead capture from external sources | Administration | Y |  |  |  | 73 | 54
X - Map third-party lead adapter forms to SmartTouch forms | Administration | Y |  |  |  | 74 | 55
Create a lead adapter to extract data from an email | Forms |  | Y |  |  | 75 | 55
Create a lead-capture form | Forms | Y |  |  |  | 76 | 56
Generate embed code for a lead-capture form | Forms | Y |  |  |  | 77 | 56
Copies form code to clipboard | Forms | Y |  |  |  | 78 | 57
View leads that submitted a form | Forms | Y |  |  |  | 79 | 57
Determine how Sales Users are notified of incoming leads | Automation | Y |  |  |  | 80 | 58
Opts to notify selected Sales Users of incoming leads | Automation | Y |  |  |  | 81 | 59
Opts to notify Sales Users of incoming leads based on rules | Automation |  |  |  | Future Release | 82 | 59
Automation Workflow | Automation | Y |  |  |  | 83 | 60
Create automation workflow to trigger actions based on an interaction | Automation | Y |  |  |  | 84 | 60
Trigger workflow when a Contact meets the criteria of a SmartSearch | Automation |  | Y |  | Line Item Estimate would be helpful.
Trigger workflow when a form is submitted | Automation | Y
Trigger workflow when a Contact's lifecycle changes | Automation | Y
Trigger workflow when a tag is applied | Automation | Y
Trigger workflow when a page is visited | Automation |  | Y
Trigger workflow when a lead score is reached | Automation |  | Y
Trigger workflow when a community is toured | Automation |  | Y
Trigger workflow when a link is clicked | Automation | Y |  |  | Required for micro-workflows attached to Campaigns
Send an email | Automation | Y
Set a delay timer | Automation | Y
Set a date timer | Automation | Y
Set a date field timer | Automation |  | Y
Add a tag | Automation | Y
Remove a tag | Automation | Y
Adjust a Contact's lead score | Automation | Y
Change a Contact's lifecycle | Automation | Y
Update a contact field | Automation | Y
Assign a Contact to a User | Automation | Y
Notify a User or Group | Automation | Y
Add a task/action/reminder | Automation | Y
Send a text message | Automation | Y
Configure micro-workflows attached to links within an email | Automation | Y |  |  |  | 85 | 62
Configure automation workflow settings | Automation | Y |  |  |  | 86 | 63
Select predefined automation workflow recipes | Automation | Y |  |  | Internal & Apps sold by partners | 87 | 63
Property | Inventory |  |  |  | Future Release | 88 | 64
Create properties | Inventory |  |  |  | Future Release | 89 | 64
Create communities | Inventory |  |  |  | Future Release | 90 | 64
X - Create property template | Inventory |  |  |  | Future Release | 91 | 64
Create a property | Inventory |  |  |  | Future Release | 92 | 65
Associate property with a person | Inventory |  |  |  | Future Release | 93 | 65
Create a document that requires a signature | Inventory |  |  |  | Future Release | 94 | 66
Manage the transaction details for a contact's purchase of a property | Inventory |  |  |  | Future Release | 95 | 68
Generate a sales contract | Inventory |  |  |  | Future Release | 96 | 68
Search for property | Inventory |  |  |  | Future Release | 97 | 69
Export property search results | Inventory |  |  |  | Future Release | 98 | 69
Events | Events |  |  |  | We may be able to create an Automation Recipe for Events. | 99 | 70
Create an event | Events |  |  |  | Future Release | 100 | 70
Activate an event | Events |  |  |  | Future Release | 101 | 72
Activate an event from the dashboard | Events |  |  |  | Future Release | 102 | 72
Activate an event from within the event record | Events |  |  |  | Future Release | 103 | 73
Add invitees to an event | Events |  |  |  | Future Release | 104 | 73
Invite a contact to an event | Contacts |  |  |  | Future Release | 22 | 25
Track invitees | Events |  |  |  | Future Release | 105 | 73
Generate a list of invitees and their appointment details | Events |  |  |  | Future Release | 106 | 74
Check-in invitees | Events |  |  |  | Future Release | 107 | 74
Reporting & Analytics | Reporting & Analytics | Y |  |  |  | 108 | 75
Reports | Reporting & Analytics | Y |  |  |  | 109 | 75
Run Smart Reports | Reporting & Analytics | Y |  |  |  | 110 | 75
Create an ad-hoc report | Reporting & Analytics | Y |  |  | Continue to enhance the functionality of custom reporting | 111 | 76
Export an ad-hoc report | Reporting & Analytics | Y |  |  |  | 112 | 78
Save an ad-hoc report | Reporting & Analytics | Y |  |  |  | 113 | 79
Save results of a search as a report | Reporting & Analytics | Y |  |  |  | 114 | 79
Access recently-run reports | Reporting & Analytics | Y |  |  |  | 115 | 80
Run a stock report | Reporting & Analytics | Y |  |  |  | 116 | 81
Add a report to the dashboard | Reporting & Analytics |  | Y |  |  | 117 | 82
Web-tracking | Reporting & Analytics | Y |  | Y |  | 118 | 82
Track web visits with Visistat | Reporting & Analytics | Y
Track web visits with custom code | Reporting & Analytics |  |  | Y | Estimate for 1.0
Generate web-tracking code | Reporting & Analytics |  |  | Y |  | 119 | 82
Copy web-tracking code to clipboard | Reporting & Analytics |  |  | Y |  | 120 | 83
Call-tracking | Reporting & Analytics |  | N | N |  | 121 | 83
Administration | Administration |  |  |  |  | 122 | 83
Login | Administration | Y |  |  |  | 123 | 83
Disables the ‘Show password as I type’ checkbox | Administration | Y |  |  |  | 124 | 84
Enters an invalid password | Administration | Y |  |  |  | 125 | 84
Enters an invalid email | Administration | Y |  |  |  | 126 | 85
Reset login credentials | Administration | Y |  |  |  | 127 | 85
Enters a valid email and requests a sign-in link | Administration | Y |  |  |  | 128 | 86
Enters an invalid password | Administration | Y |  |  |  | 129 | 86
Setup & Customization | Administration | Y |  |  |  | 130 | 86
Create a new account | Administration | Y |  |  |  | 131 | 86
Continue configuration within customer’s account | Administration | Y |  |  |  | 132 | 87
Send contact a welcome email | Administration | Y |  |  |  | 133 | 87
On-board new account | Administration | Y |  |  |  | 134 | 87
Modify the dashboard | Administration |  | Y |  |  | 135 | 88
Modify labels | Administration |  | Y |  |  | 136 | 89
Rearrange contact fields | Administration |  | Y |  |  | 137 | 90
Configure lead scoring | Administration | Y |  |  |  | 138 | 91
Create custom fields | Administration | Y |  |  |  | 139 | 94
Select and rearrange columns in a table | Administration |  | Y |  |  | 140 | 95
User selects and rearranges columns in a table | Administration |  | Y |  |  | 141 | 96
Set default pagination for tables | Administration | Y |  |  |  | 142 | 96
Create shortcut links | Administration |  | N |  |  | 143 | 96
Internationalize form elements | Administration | Y |  |  |  | 144 | 97
Localize SmartTouch | Administration | Y |  |  |  | 145 | 97
Link social media accounts with SmartTouch | Administration | Y |  |  |  | 146 | 98
Import a list of data | Administration | Y |  |  |  | 147 | 99
Rollback importing data | Administration |  |  | N |  | 148 | 100
Search for and merge duplicate data | Administration |  |  | N | Discuss | 149 | 101
Document Library | [5 empty] | 150 | 103
Add a commonly-used document | [5 empty] | 151 | 103
Roles and Permissions | Administration | Y |  |  |  | 152 | 104
Create roles and permissions | Administration | Y |  |  |  | 153 | 104
Identify a contact as a SmartTouch user | Administration | Y |  |  |  | 154 | 105
Change a user’s role via setup | Administration | Y |  |  |  | 155 | 105
Change a user’s role via their contact record | Administration | N |  |  |  | 156 | 105
Integrations | Integrations | Y |  |  |  | 157 | 106
Gmail | Integrations | Y
Google Calendar | Integrations | Y
Office365 | Integrations | Y
Outlook 2007 (or maybe 2010?) | Integrations | Y
Google Maps | Integrations | Y
Zillow Homes | Integrations | Y
Email lookup | Integrations | Y
Note on C170: Grant Taylor: No longer applies because we change the layout for Contacts