## Final Punch List for SEP
MODULE NAME | DESCRIPTION | TYPE | SCOPE STATUS | PRIORITY
Sign-in | Prevoius Password Set-up Validation | Pending Functionality | In-Scope
Sign-in | 1211- Session out should not happen when user accessing the application which is opened in two or more tabs and operating in one tab | Bug | In-Scope
Sign-in | 353 - Able to Login with previous Password - After Resetting the New Password | Bug | In-Scope
Sign-in | 460 - After logout of smarttouch application if we click on back button beside address bar its displaying the previous Screen | Bug | In-Scope
Sign-in | 2047 - Throwing "500 internal error" when logging after session expire. | Bug | In-Scope
Top-Navigation | Add - Add Opportunity into Quick Links | Pending Functionality | In-Scope |  | Added New With Opportunity Module
Top-Navigation | Recent Activities - Details View | Pending Functionality | In-Scope
Top-Navigation | Notifications - Additional Areas Like - Opportunities, Owner Assignment, Campaigns Sent, and Other Areas Needs to Include | Pending Functionality | In-Scope |  | Need Provide Details
Top-Navigation | Load Recent Activities in Async | Pending Functionality | Not In Scope
Top-Navigation | Include Privacy policy - Integration into Profile Menu - 2124 | New | Not In Scope
Top-Navigation | Notifications to Include Profile Based Settings - Integration - Lead Score based Configuration for Text/ Email & Notification Section | Pending Functionality | In-Scope
Top-Navigation | Recent Activities - If Single Contact is Updated 4 times - displays as 4 Contacts Have been updated - while those should be grouped by contact | Bug | In-Scope
Top-Navigation | Include Saved Searches into Recent Activities | Pending Functionality | In-Scope
Header | Account Logo - Integration | Pending Functionality | Not In Scope
Header | User Profile / Name and Role Display based on the New design | Pending Functionality | Not In Scope
My Profile | 2281 : Email signature is saving successfully with out selecting the Email_id from 'Email Address' drop-down | Bug | In-Scope
My Profile | Alert Notification- On the Campaign Link Engagement | Pending Functionality | In-Scope
My Profile | Notification - Profile Based Configuration Settings - Additional Settings - for Lead Score Based Engagement Configuration | Pending Functionality | In-Scope
My Profile | Integrations - Google, Google Calender, Facebook, Twitter - Interation for Login for Profile | Pending Functionality | In-Scope
My Profile | Pagination - Not Refelecing in Opportunities Grid | Pending Functionality | In-Scope
My Profile | Time Zone - Settings based Time Display in Timeline not Implemented - Both Account level and User Level | Pending Functionality | In-Scope
Account Settings | Configuration, Data Sharing - Have Module Icons for Module Level Toggels, 2190 - Verify | New | Not In Scope
Account Settings | 2258 - Zillow Account's 'Notifications' and 'Recent Activities' are displaying to ST-Admin | Bug | In-Scope
Account Settings | 338 - Email should not send to Account holder if the Account Admin create the Account in the Paused mode ; Also Do not have defined status Values for account | Bug | In-Scope
Account Settings | 234 - In Add Account when user "Create Account" button with out enter mandetory fields screen position should move top to display the alerts to the user at the respective fields | Bug | In-Scope
Account Settings | Auto Incerement of Available Address, Social and Phone Types while adding contact or Account - both in contacts Module and Accounts Module | Bug | In-Scope
Account Settings | 2279 - When clicking on 'Cancel' button in 'Data Sharing' and 'Basic Info' screen its showing access denied page to account admin | Bug | In-Scope
Admin Notification | Module to Take the Notification Title and Message from ST Super Admin and Publish to all Account Admin's or All Users from All Accounts or specific Accounts | New Functionality | Not In Scope
Account Configuration - Users | 230 - In list of All Users Grid when multiple records are checked for resend invite if there exists a record which is already registered then alert is not displaying to the user that record is already registered | Bug | In-Scope
Account Configuration - Users | 229 - In Users if we "Resending" Email to multiple users then in sucess message need to display the count that number of records are checked | Bug | In-Scope
Account Configuration - Users | New user Created - Un Registered Mode - Email Should be sent with Link; Once Email is verified by User - Active ; and Admin can In active the User - Based on This flow the Showing filter should contain - Unregieted in the dropdown list - also Resend Invite has to work for only users with Un-Regstered Status. | New | In-Scope / Enhancement
Account Configuration - Users | 2210 - When adding a user which is already deleted, it's displaying an alert "Contact already present". | Bug | In-Scope
Account Configuration - Roles | Role Based - Module Display and Accibility setting - Not Implemented as per the discussions and document shared - refer Document sent by Pavan - Also Module level Grouping | Enhancement | Enhancement
Account Configuration -Custom Fields | Enter Button Should work for Submitting the changes for Areas with Tick Options | Bug | In-Scope
Account Configuration -Custom Fields | If Custom Field Created with type as dropdown - ID's are displayed where as values should display after saving the custom fields and used | Bug | In-Scope
Account Configuration -Custom Fields | 2256 - Hide option-'Add Custom Tab' when User is configuring a custom field | Bug | In-Scope
Account Configuration -Custom Fields | 2267 - Custom Tabs are saving with Spaces and Special Charecters | Bug | In-Scope
Account Configuration -Custom Fields | 2309 - Fields which are deleted in custom fields are still displaying while adding internet form. | Bug | In-Scope
Account Configuration - Lead Score | Apply for Previous Actions - Functional Validation and Impelementation | Pending Functionality | In-Scope
Account Configuration - Lead Score | 1189 - Live Search of Tags should be based on Event Trigger Specifc to Actions or Tours Selected | Bug | In-Scope
Account Configuration - Lead Score | Include additional Triggers actions like - Campaigns, Websites, - Clicks and Visits | Pending Functionality | In-Scope
Account Configuration - Lead Score | 2265 - for Trigger - Note with the Following tag - is applied only once - but this should apply any time the activity is created that implies the rule - this includes, Actions, Tours, Notes | Bug | In-Scope
Account Configuration - Import Data | Unable to import the file for Further validation | Pending Functionality | In-Scope
Account Configuration - Import Data | Field level Validation for Data Types Needs to Include | Enhancement | Enhancement
Account Configuration - Import Data | 2031, 1190,1156,1107,1023,1018, 1015,1014,1012 | Bugs | In-Scope
Account Configuration - Lead Adaptors | Full Functional level Fixed Needs to be Developed | Pending Functionality | In-Scope
Account Configuration - Lead Adaptors | 1405,1394,1210,1208,1206,1205,1204,1154,1019,1010 | Bugs | In-Scope
Account Configuration - Manage Tags | 2282,999, 1026, 1003 | Bugs | In-Scope
Account Configuration - Dropdown Fields | Dsipaly Sort Number - Read Only - Have Darg and Drop for Sorting | Enhancement | Enhancement
Account Configuration - Dropdown Fields | 2263,2261,2243,2203, 2212 | Bug | In-Scope
Application | URL - Reformatting - 1129, | Enhancement | Enhancement
Application | UI Control Design Changes for Multi Dropdown Select and Radio Buttons - 1116 | Pending Functionality | In-Scope
Application | IE Browser Level Issues - 960 | UI - Fixes | In-Scope
Timeline | Month Display and Total Activities Count - UI update | UI - Fixes | In-Scope
Basic Search | 2127, 2143, 2273 | Bug | In-Scope
Grid Search | Tags Not, Custom Fields Included in Grid Searches | Pending Functionality | Enhancement
Basic Search | on Tags Result Dsiplay - Click on the Tag should take to Results Contacts Grid | Pending Functionality | In-Scope
Basic Search | Search Results UI - BG shows Black Color | UI - Fixes | In-Scope
Basic Search | Serach Should Incllude - Custom Fields | Pending Functionality | In-Scope
Advance Search | 2150, 2152, 2246, 2248,2257,2268 | Bug | In-Scope
Advance Search | All Operators and Logicial Operators Should be Displayed in CAPS | Bug | In-Scope
Advance Search | Custom Filter Logic - Should Auto Populate | Pending Functionality | In-Scope
Advance Search | Filters Should Include additional Fields - Custom Fields both in Fileters and Results | Pending Functionality | In-Scope
Advance Search | Search Name Validation on Save of Search Should High Light | Bug | Enhancement
Advance Search | Export to Excel and Export to PDF of Search Results | Pending Functionality | In-Scope
Application | Contacts Grid Should have Standard Fields across - Contacts , Search Results and Reports | Bug | Enhancement
Contacts Grid | Recently Viewed Contacts and My Contacts Needs to be Fixed | Pending Functionality | In-Scope
Contacts Grid | 365, 2033 | Bug | In-Scope
Contacts Grid | Send Email Not Opening in Pop-up | Pending Functionality | In-Scope
Contacts Grid | Last Touched Info not disolaying in Grid | Pending Functionality | In-Scope
Add /Edit Contact | 2235,2237,2238, 2276 | Bug | In-Scope
View Contacts | Engagement Section - Not Implemented | Pending Functionality | In-Scope
View Contacts | 2278, | Bug | In-Scope
Company Contact - View | Opportunity Analytics Section | Pending Functionality | Enhancement
Company Contact - View | Display Number of Employees Associated | Pending Functionality | In-Scope
Company Contact - View | Opportunity Analytics Section | Pending Functionality | Enhancement
Company Contact - Add / Edit | Opportunity B2B Integration with Company Contact | Pending Functionality | Enhancement
Company Contact - View | Peoples Widget with list of Employees Associates | Pending Functionality | Enhancement

## Punchlist - 09012014
MODULE NAME | DESCRIPTION | TYPE | SCOPE STATUS | PRIORITY | DEV COMPLEXITY | DEVELOPER | DEV Review Comments | Business Review Comments
Sign-in | Prevoius Password Set-up Validation - for last 3 Similar Passwords , Login Audit Needs to be implemented | Pending Functionality | In-Scope | HIGH |  | Avinash
QuickLinks | Add - Add Opportunity into Quick Links | Pending Functionality | In-Scope | HIGH |  | Avinash
Recent Activities | Recent Activities - Details View | Pending Functionality | In-Scope | HIGH |  | Bharath
Recent Activities | Recent Activities - If Single Contact is Updated 4 times - displays as 4 Contacts Have been updated - while those should be grouped by contact | Pending Functionality | In-Scope | HIGH |  | Bharath
Recent Activities | Include Saved Searches into Recent Activities | Pending Functionality | In-Scope | HIGH |  | Avinash
Notifications | Notifications - Additional Areas Like - Opportunities, Owner Assignment, Campaigns Sent, and Other Areas Needs to Include | Pending Functionality | In-Scope | HIGH |  | Bhavani
Notifications | Notifications Implemented based on profile settings - Alert Notification- On the Campaign Link Engagement | Pending Functionality | In-Scope | HIGH |  | Avinash
Top-Navigation | Include Privacy policy - Integration into Profile Menu - 2124 | New Functionality | Not In Scope | MEDIUM |  | Hari |  | This is a New Functionality Not in ISD to display the Privacy Policy Per Account - in the User Menu / Footer / Campaign / Transactional Emails
Header | Account Logo - Integration | New Functionality | Not In Scope | LOW |  | Hari |  | Provide account a section to upload their company logo and Display Logo in the Header once the account level users login
Header | User Profile / Name and Role Display based on the New design | New Functionality | Not In Scope | LOW |  | Hari |  | Display Logged in User Name and Role Under the My Profile Menu - UI as per mahesh Provided
My Profile | Integrations - Google, Google Calender, Facebook, Twitter - Interation for Login for Profile | Pending Functionality | In-Scope |  |  | Hari |  | Need to Discuss and Identify if we need to have these built integrated into Campaigns and Other social Sections under this common area
My Profile | Time Zone - Settings based Time Display in Timeline not Implemented - Both Account level and User Level | Pending Functionality | In-Scope |  |  | Avinash
Account Settings | Configuration, Data Sharing - Have Module Icons for Module Level Toggels, 2190 - Verify | New Functionality | Not In Scope | LOW |  | Avinash |  | This is Good to have since plain Names does not look good - Mahesh to provide the design view
Admin Notification | Module to Take the Notification Title and Message from ST Super Admin and Publish to all Account Admin's or All Users from All Accounts or specific Accounts | New Functionality | Not In Scope | LOW |  | Hari |  | This is a New Functionality Decided based on meetings - Not in ISD - Good to Have feature can be build before December
Account Configuration - Users | New user Created - Un Registered Mode - Email Should be sent with Link; Once Email is verified by User - Active ; and Admin can In active the User - Based on This flow the Showing filter should contain - Unregieted in the dropdown list - also Resend Invite has to work for only users with Un-Regstered Status. | Pending Functionality | Enhancement | HIGH |  | Hari |  | - This is the Flow defined for the New Users Getting Registed to the account - Requires Additional User Status "Un-Registered". - Validation on Resend Invite for only Un Registered Users
Account Configuration - Roles | Role Based - Module Display and accessibility setting - Not Implemented as per the discussions and document shared - refer Document sent by Pavan - Also Module level Grouping | Pending Functionality | Enhancement | HIGH |  | Hari |  | For Account Admin - Under Roles - Do not Display "Account Admin" or "ST Admin" Role. Roles Has be Grouped Under Module Levels Please Refer - Email from Pavan on the discussiosn and decisions made to implement
Account Configuration -Custom Fields | Enter Button Should work for Submitting the changes for Areas with Tick Options | UI - Fixes | In-Scope | MEDIUM |  | Mahesh |  | Record this as Bug
Account Configuration -Custom Fields | Pending Custom Fields to Implement under custom fields - 1. Text area 2. Multi-select Dropdown ( Technical Conflict with Default HTML Controls - Will define this at later Phases) 3. Check Box Sorting form fields Additional Fields Provided 1.Radio 2.Email 3.URL | Pending Functionality | In-Scope | HIGH |  | Siva
Account Configuration - Lead Score | Apply for Previous Actions - Functional Validation and Impelementation | Pending Functionality | In-Scope | MEDIUM |  | Hari |  | As per the meeting with Grant and Reviews we had - Following is the Requirement When "Apply to Previous is Checked" - For all the contacts who satisfies the Lead Score Rule that got created at that specific time , Needs to be updated with the Score defined in the rule. - If rule gets created with the Option Checked - While Editing the Rule Needs to have the Option checked and Does not allow to un-check -
Account Configuration - Lead Score | Include additional Triggers actions like - Campaigns, Websites, - Clicks and Visits | Pending Functionality | In-Scope | HIGH |  | Bharath
Account Configuration - Import Data | Unable to import the file for Further validation | Pending Functionality | In-Scope | HIGH |  | Srinivas
Account Configuration - Import Data | Field level Validation for Data Types Needs to Include | Enhancement | In-Scope | MEDIUM |  | Hari |  | Under Imports in Mapping Section - There needs to be a validation for Data Types for the Contact Field to the Import file field Data type
Account Configuration - Lead Adaptors | Full Functional level Fixed Needs to be Developed | Pending Functionality | In-Scope | HIGH |  | Srinivas
Account Configuration - Dropdown Fields | Display Sort Number in Read Only and have Darg and Drop for Sorting | Pending Functionality | In-Scope | MEDIUM |  | Hari |  | Display Number and Drag and Drop were Original requirements - While after review the update is to have Number Readonly and Have Darg and Drop for Soring
Application | URL - Reformatting - | Enhancement | Enhancement | HIGH |  | Hari |  | All the URL's Naming covention and Encoding of URL's needs to be done
Application | UI Control Updates for RadioButton, Multi Select Drop Down | Pending Functionality | In-Scope | MEDIUM |  | Bharath/Mahesh
Grid Search | Tags & Custom Fields Included in Grid Searches | Pending Functionality | Enhancement | HIGH |  | Hari |  | We need to include Tags and Custom Fields at every module level to include in the Grid Search Elements - Not Specified in ISD
Basic Search | On Tags Result Dsiplay - Click on the Tag should take to Results Contacts Grid | Pending Functionality | In-Scope | HIGH |  | Srinivas
Basic Search | Search Results UI - BG shows Black Color | UI - Fixes | In-Scope | MEDIUM |  | Mahesh |  | Record this as Bug
Advance Search | Custom Filter Logic - Should Auto Populate | Pending Functionality | In-Scope | HIGH |  | Srinivas
Advance Search | Filters Should Include additional Fields - Custom Fields both in Filters and Results | Pending Functionality | In-Scope | HIGH |  | Pavan |  | As discussed in the Advanced Search both in Filters and in the Columns Section of Search Results Should inclue All Contacts Fields and Custom Fields associated
Advance Search | Export to Excel and Export to PDF of Search Results | Pending Functionality | In-Scope | HIGH |  | Srinivas
Application | Contacts Grid Should have Standard Fields across - Contacts , Search Results and Reports | Pending Functionality | Enhancement | HIGH |  | Pavan |  | As per the discussions the fields in the search results and Contacts Grid should be standard - Hence display fields in contacts grid as standard result set for search results
Contacts Grid | Recently Viewed Contacts and My Contacts Needs to be Fixed | Pending Functionality | In-Scope | HIGH |  | Bharath
Contacts Grid | Send Email Not Opening in Pop-up in Contacts Grid or in Contact View and able to send email | Pending Functionality | In-Scope | HIGH |  | Haritha/ Bhavani |  | Report this as Bug
Contacts Grid | Last Touched Info not displaying in Grid | Pending Functionality | In-Scope | HIGH |  | Bharath
View Contacts | Engagement Section - Not Implemented | Pending Functionality | In-Scope | HIGH |  | Bhavani
Company Contact - View | Opportunity Analytics Section | Pending Functionality | Enhancement | HIGH |  | Srinivas
Company Contact - View | Display Number of Employees Associated | Pending Functionality | In-Scope | HIGH |  | Hari |  | Will need to discuss on the design approach to do this
Company Contact - View | Peoples Widget with list of Employees Associates | Pending Functionality | Enhancement | HIGH |  | Pavan |  | Same as Above - will define based on the above decision making
Company Contact - Add / Edit | Opportunity B2B Integration with Company Contact | Pending Functionality | Enhancement | HIGH |  | Bhavani |  | Only Change here is based on the Opportunity - Settings in Configuration If the setting is configured for "PEOPLE" - Allow to include Individuals into buyers if the setting is configured for "COMPANY" - Allow to include Companies into buyers
Company Contact - View | Pending in Timeline - Activities selection; Period dropdown when Custom is selected; Alignment for the month and record display, Delete Note | Pending Functionality | In-Scope | HIGH |  | Srinivas
Company Contact - View | Do not email, Address Type, Street 1, Street 2, City, State, Zip Code, Country - fields are to be listed under Company Info tab | Pending Functionality | In-Scope | HIGH |  | Naresh
Company Contact - View | Issue with google drive integration | Pending Functionality | In-Scope | HIGH |  | Avinash
Company Contact - View | Missing functionalities in the right hand pane for opportunities | Pending Functionality | In-Scope | HIGH |  | Bhavani
Company Contact - View | The following functionalities are to be covered: Add Opportunity not covered. Export Company not covered. | Pending Functionality | In-Scope | HIGH |  | Srinivas
Company Contact - View | Missing functionality - If any address field (Street, City, State, or Zip) is populated, then the other fields are also required. | Pending Functionality | In-Scope | MEDIUM |  | Pavan
Add Action | The following functionalities are missing in Reminder Method field - 1. Email 3. Text to [User’s mobile number] | Pending Functionality | In-Scope | HIGH |  | Avinash
Add Action | Save & Mark Complete - button is to be included | Pending Functionality | In-Scope | HIGH |  | Bhavani
Add Action | Date and Time are required if ‘Specific date & time’ is selected in ‘Complete by’ | Pending Functionality | In-Scope | HIGH |  | Avinash
Add Tag | Tag Help icon is to be included. | Pending Functionality | In-Scope | HIGH |  | Bhavani
Add Tour | The following functionalities are missing in Reminder Method field - 1. Email 3. Text to [User’s mobile number] | Pending Functionality | In-Scope | HIGH |  | Avinash
Add Tag | Add Tag Button - Disabled by default. Enable when tag is entered or selected | Pending Functionality | In-Scope | HIGH |  | Pavan
Campaigns List | Delivery Rate, Clicked Rate, Open Rate - functionality is to be added | Pending Functionality | In-Scope | HIGH |  | Bharath
Campaign Layout | Send Campaign - Applies if all steps have been completed, Editable option in HTML apart from readable mode | Pending Functionality | In-Scope | MEDIUM |  | Pavan |  | Yes, Send Campaign will work only if all the mandatory fields are provided.
Campaign Customize | Customize functionality in campaign is to be covered | Pending Functionality | In-Scope | HIGH |  | Siva
Campaigns_Review & Send | Social (Accordion) functionality isn't covered | Pending Functionality | In-Scope | HIGH |  | Siva
Visistat Integration | Integration to visistat for Webiste Visits and Clicks Tracking |  | In-Scope | HIGH |  | Bharath
VMTA - Response Capture & Campaigns Integration | VMTA .net Integration for Sending Campaigns and Response Tracking and Updating Campaign Dashboard |  | In-Scope | HIGH |  | Bharath
Communication Configuration | Account Admin Interface for Configuring the - Sender ID's for - Email ( Campaign / Transactional ) , Text - As per the email forwarded |  | In-Scope | HIGH |  | Bharath / Siva
Forms | Forms - Sorting Form Fields |  | In-Scope | MEDIUM |  | Siva
Custom Fields Mapping in Imports / Lead Adaptors | Custom Fields Mapping in Imports / Lead Adaptors |  | Not In Scope | MEDIUM |  | Srinivas
Email Preferances | Email Preferences Section for users to un subscribe for campaigns |  | Not In Scope | HIGH |  | Siva